Stages for Unsolicited LOI’s

U01/N01: 		For all unsolicited LOI’s (Phase 1 and Phase 2)

Cooperative Groups: 	For Unsolicited Phase 1 LOI’s with a CTEP IND and for

Unsolicited Phase 2 LOI’s with a CTEP IND and with <100 patients

For Unsolicited Phase 1 or Phase 2 LOIs <100 patients NOT under CTEP IND will have similar timeline, but components of timeline will be a bit different

All times in calendar days

Stage 1: LOI Development (Total stage 60 days: Day 1 to 60)

Stage 1a:	Initial LOI Consensus Evaluation:

30 Days   	 (Day 1 – Day 30)

Beginning Milestone: 		LOI receipt

Ending Milestone:	Consensus Review sent to PI

If approved, advance to Stage 2.

Stage 1b:	Follow-Up for LOI’s On-Hold and LOI Approval:

30 Days  	  (Day 30 – Day 60)*

Beginning Milestone:		Consensus Review sent to PI

Ending Milestone:		LOI approval

*Time-out for: drug commitment and industry approval

Stage 2: Protocol Development (Total stage 60 days: Day 61 to 120)

60 Days  	  (Day 61 – Day 120)

Beginning Milestone:		LOI approval

Ending Milestone:		Protocol receipt

Stage 3: Protocol Approval (Total stage 90 days: Day 121 to 210)

Stage 3a:	Initial Protocol Consensus Evaluation:

30 Days 	   (Day 121 – Day 150)

Beginning Milestone:		Protocol receipt

Ending Milestone:		Consensus Review sent to PI

Stage 3b:	Follow-Up Consensus Evaluations:

35 Days 	  (Day 150 – Day 185)

Beginning Milestone:		Consensus Review sent to PI

Ending Milestone:		Protocol approval on-hold

Stage 3c:	Protocol Approval and Activation:

25 Days   	 (Day 185 – Day 210)*

Beginning Milestone:		Protocol approval on-hold

Ending Milestone:		Protocol activation

*Time-out for: IRB approval and possibly for FDA review

| Unsolicited LOI's |  |  |  |
| --- | --- | --- | --- |
| Stages | Document Milestone Tag for Tracking | Total Planned # of Calendar Days for Stage | Responsible Party |
| Initial LOI Consensus Evaluation | LOI receipt date in CTEP PIO | 30 | Site/Group |
|  | IDB review date |  | CTEP |
|  | PRC review date |  | CTEP |
|  | LOI on hold pending revision |  | CTEP |
|  | Consensus Review completed (LOI) |  | CTEP |
|  | Consensus Review sent to PI |  | CTEP |
| Follow-Up for LOI's On-Hold and LOI Approval | Conference call with IDB lead and PI | 30 | Both |
|  | Revised LOI submitted |  | Site/Group |
|  | IDB review date |  | CTEP |
|  | PRC review date |  | CTEP |
|  | LOI on hold pending revision |  | CTEP |
|  | Consensus Review completed (LOI) |  | CTEP |
|  | Consensus Review sent to PI |  | CTEP |
|  | LOI on hold pending industry approval |  | CTEP |
|  | Timeout for drug commitment/industry approval - begin |  | Time-out: CTEP |
|  | Timeout for drug commitment/industry approval - end |  | Time-out: CTEP |

*Shaded milestones do not contribute to the stage’s total number of days but do count towards the drop dead date

| Stages | Documents Milestone Tag for Tracking | Total Planned # of Calendar Days for Stage | Responsible Party |
| --- | --- | --- | --- |
| Protocol Development | Protocol receipt date | 60 | Site/Group |
| Initial Protocol Consensus Evaluation | Protocol reviewed at PRC | 30 | CTEP |
|  | Protocol on hold pending revision |  | CTEP |
|  | Consensus Review sent to PI |  | CTEP |
| Follow-Up Protocol Consensus Evaluations | Conference call between CTEP and PI | 35 | Both |
|  | Revised Protocol submitted |  | Site/Group |
|  | Protocol reviewed at PRC |  | CTEP |
|  | Protocol on hold pending revision |  | CTEP |
|  | Consensus Review sent to PI |  | CTEP |
|  | Protocol 'approved on hold' |  | CTEP |
| Protocol Approval and Activation | Timeout for IRB approval - begin | 25 | Time-out: Site/Group |
|  | Timeout for IRB approval - end |  | Time-out: Site/Group |
|  | Timeout for FDA review - begin |  | Time-out: CTEP |
|  | Timeout for FDA review - end |  | Time-out: CTEP |
|  | Protocol activated |  | Site/Group |

*Shaded milestones do not contribute to the stage’s total number of days but do count towards the drop dead date